## Slide 1
EWMA Covariate
Shift Demo
Manuscript and implementation review
Auditable CSE reconstruction for motor-imagery EEG
Writing, coding, and literature progress
28 September 2026
Scope: CSE subsystem and classifier benchmark
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 2
PROGRESS SNAPSHOT
Writing, code, and literature now align
The abstract defines a configuration-controlled CSE baseline
The detector, data boundaries, and classifier benchmark are described separately with an incoming full adaptive-learning loop.
2A
Session I development
Session II held out
2B
Sessions I–III development
Sessions IV–V held out
2
detector stages:
EWMA and Hotelling T²
Current maturity
CSE reconstruction and method audit
hlin863/ewma_covariate_shift_demo
02
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 3
LITERATURE REVIEW
Reading informs the reconstruction and its limits
2015
Raza: detector basis
EWMA warning logic
D2 reconstruction
2018
Chowdhury: online BCI
FBCSP setting
Cohort and feedback
2019
Raza: CSE-UAEL
Two-stage CSE
Adaptation context
Related
Rao and Heyden
PCA interpretation
Change detection
The literature review separates published detector methods from reconstruction choices and proposed extensions.
hlin863/ewma_covariate_shift_demo
03
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 4
IMPLEMENTED PIPELINE
CSE ends at validated shift evidence
BCI data
Cue-aligned trials
2A and 2B
Signal representation
10-band FBCSP
PCA scores
Stage I
EWMA candidate
warnings
Stage II
Hotelling T²
validation
Evidence
Counts, diagnostics
and provenance
CSE subsystem boundary
The classifier benchmark is a separate experiment. Shift-triggered pseudo-labelling and ensemble growth remain future work.
hlin863/ewma_covariate_shift_demo
04
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 5
DATA PROTOCOL
Feature fitting is confined to development training
BCI Competition IV 2A
Session I develops the model
Split Session I into training and validation
Fit FBCSP on training trials only
Apply fitted features to validation trials
Reserve Session II for held-out evaluation
BCI Competition IV 2B
Sessions I–III develop the model
Stratified 70/30 training–validation split
Fit FBCSP on development training only
Apply fitted features to validation trials
Reserve Sessions IV–V for evaluation
Shared rule
Evaluation trials do not enter feature-model fitting.
Report detector outputs with the configuration that produced them.
hlin863/ewma_covariate_shift_demo
05
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 6
CODING AND VERIFICATION
A real-data benchmark now complements CSE tests
2
classifier strategies
Linear SVM and bootstrap-aggregated
Linear-SVM ensemble on 2A and 2B
Data boundaries
train, validation, and held-out evaluation roles
Feature pipeline
cue-aligned extraction, FBCSP, and PCA
Detector audit
λ, control limits, variance, and window eligibility
Benchmark
single SVM versus bagged linear-SVM ensemble
Verification
automated tests and targeted numerical checks
Synthetic experiments verify software behaviour; real-data comparisons supply the research benchmark.
hlin863/ewma_covariate_shift_demo
06
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 7
MANUSCRIPT STATUS
Abstract claims match the implemented scope
Written now
EEG non-stationarity
CSE rationale
2A and 2B data roles
FBCSP fitting boundary
Detector stages
Method audit
PCA dimension
EWMA variance updates
Control limits
Stage-II window eligibility
Configuration provenance
Next evidence
Configuration-locked counts
Subject-level comparison
Classifier benchmark results
Error and delay trade-offs
Selective adaptation criteria
Current claim
Auditable CSE reconstruction with a separate classifier benchmark; numerical agreement remains to be established.
hlin863/ewma_covariate_shift_demo
07
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 8
PROJECT TIMELINE
First-year plan: six overlapping work packages
Proposed October 2026 – September 2027 schedule, aligned with the requirements document
TIMING
WORK PACKAGE AND SCOPE
EXPECTED OUTPUT
M1–3
Oct–Dec 2026
WP1 Theory and architecture
CPD–CL–twin design, stability and update budgets
Architecture specification
M2–5
Nov 2026–Feb 2027
WP2 CPD benchmarking
EWMA, CUSUM, BOCPD and density-ratio methods
Benchmark suite and report
M4–7
Jan–Apr 2027
WP3 Continual learning and sustainability
Regularisation, replay, forgetting and energy costs
CL module and cost analysis
M5–9
Feb–Jun 2027
WP4 Digital-twin co-evolution
Twin disagreement, joint updates and safety checks
Twin framework and testbed
M7–11
Apr–Aug 2027
WP5 Cross-domain evaluation
BCI and photonic manufacturing maintenance
Results against retraining
and periodic-update baselines
M10–12
Jul–Sep 2027
WP6 Synthesis and engagement
Manuscripts, open release and stakeholder work
Submissions and
adoption roadmap
The present CSE reconstruction supports WP1–2; later work tests selective adaptation and update costs.
hlin863/ewma_covariate_shift_demo
08
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.

## Slide 9
NEXT MILESTONE
Lock configurations and trace each result
Evidence to complete
Record train, validation and evaluation provenance
Fix PCA, λ, and control-limit settings
Report warnings and confirmations by subject
Compare classifier strategies on held-out data
Next manuscript result
Configuration-locked reproduction table
Paper section
Method
Code
Experiment
Result
Immediate action
Link each reported count and benchmark result to its dataset split, code path and detector configuration.
hlin863/ewma_covariate_shift_demo
09
Notes: Update grounded in the author-supplied abstract (28 September 2026) and the source progress review deck.